## Cover
Chapter 14 Staffing Plan v. 6.0 21 December 2018
© epic, 2017

## Document control & content
Document Control: Staffing Plan
Version History
Version | Date | Comments
1 | 2017-02-28 | Initial release (epic, Alan Shaw)
1.1 | 2017-04-28 | 2nd release (epic, Alan Shaw); changes between 1 March - 27 Apr 2017
2 | 2017-06-15 | 3rd release (epic, Alan Shaw); changes between 28 Apr - 15 Jun 2017
2.1 | 2017-07-15 | Master Plan, v. 1.0
3 | 2017-12-15 | Changes between 16 July - 15 Dec 2017; tech equipment, source changes, delayed start dates
4 | 2018-03-15 | Changes between 1 Jan - 15 March 2018
5 | 2018-06-15 | Changes since 15 March; start dates adjusted; some quantity reductions
5.1 | 2018-08-15 | Proposed new plan for simplified Games Delivery
6 | 2018-12-21 | Revised plan per Commissioner submitted for Staffing Agency tender
Content
Sheet |  | Description
Staffing plan |  | Projected ARU staffing plan for all FAs and job titles noting assumed and estimated quantity, source, salary, start and end dates, length of service and total compensation; summary charts indicating compensation ranges, total quantities and costs by FA, staff type and source summaries

## Staffing Plan Master
Napoli 2019 Staffing Plan
No. | Qty | FA | Position | Hired | Planned to be hired by… | [5 empty] | Seat at HQ |  | Tech equipment |  |  | Venue | Approx. Monthly Salary | Target Start Date | Practical End Date (tbc) | Length of Hire | Total Compensation | Name if Hired or In process | GIORNI/ UOMO | mesi | numero |  | Comment
[5 empty] | IFEL | Private Company | Tender | Staffing Agency | Direct (>40k) | Service Provider | ARU 1, 2, 3 | ARU 4 | Desktop | Laptop | Mobile phone | Radio
1 | 1 | ACR | Head of Accreditation | 1 | [6 empty] | 1 |  |  | IFEL | Voda |  | 6000 | 2019-03-04 | 2019-08-31 | 0.49167 | 35400 | M. Galloni
2 | 1 | ACR | Manager, Accreditation Ops |  | 1 | [5 empty] | 1 |  |  | IFEL | 1 |  | 3500 | 2019-03-18 | 2019-08-15 | 0.40833 | #REF! |  | 150 | 6 | 1 | 21000
3 | 1 | ACR | Coordinator, Client Accreditation |  |  |  | 1 |  |  |  | 1 |  |  | 1 | 1 |  | 3500 | 2019-03-18 | 2019-08-15 | 0.40833 | #REF! |  | 150 | 6 | 2 | 42000
4 | 1 | ACR | Coordinator, Client Accreditation |  |  |  | 1 |  |  |  | 1 |  |  | 1 | 1 |  |  | 2019-03-18 | 2019-08-15
5 | 1 | ACR | Accred Specialist (Workforce/ITO/NTO) |  |  |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 2500 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 6 | 2 | 30000
6 | 1 | ACR | Accred Specialist (Workforce/ITO/NTO) |  |  |  | 1 |  |  |  | 1 |  | 1 |  |  |  |  | 2019-04-15 | 2019-07-31
7 | 1 | ACR | Accred Specialist (Delegations) |  |  |  | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2019-04-01 | 2019-07-31
8 | 1 | ACR | Accred Specialist (FISU Family, Media) |  |  |  | 1 |  |  |  |  | 1 | 1 |  |  |  | 2500 | 2019-04-15 | 2019-07-31 | 0.29444 | #REF! |  | 107 | 5 | 2 | 25000
9 | 1 | ACR | Accreditation Ctr Spvr (MAC @ AVN) |  |  |  | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2019-05-01 | 2019-07-31
10 | 1 | ACR | Accreditation Ctr Spvr (Workforce/ITO/NTO) |  |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2019-04-15 | 2019-07-31
11 | 1 | ACR | Accreditation Ctr Spvr (FISU Family hotel) |  |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2019-05-15 | 2019-07-31
12 | 1 | ACR | Accreditation Ctr Spvr (MPC) |  |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 2500 | 2019-05-15 | 2019-07-31 | 0.21111 | #REF! |  | 77 | 4 | 4 | 40000
|  |  | Sub total | 1 | 1 | 0 | 7 | 3 | 0 |  | 6 | 6 | 8 | 2 | 3 | [5 empty] | #REF! |  |  |  |  | 0
1 | 1 | AVM | Head of Athletes' Village Management | 1 | [6 empty] | 1 |  |  | IFEL | Voda |  | 6000 | 2019-03-01 | 2019-09-15 | 0.53889 | #REF! | A. Roca |  |  |  | 0
2 | 1 | AVM | Manager, AV Napoli (AVN) | 1 | [6 empty] | 1 |  |  | IFEL | Voda |  | 5000 | 2019-03-04 | 2019-08-30 | 0.48889 | #REF! | P. Melloni | 179 | 7 | 1 | 35000 | Remove from Pvt Company hire list
3 | 1 | AVM | Manager, AV Salerno (AVS) | 1 | [6 empty] | 1 |  |  | IFEL | Voda |  | 5000 | 2019-03-04 | 2019-08-30 | 0.48889 | #REF! | F. Temporelli | 179 | 7 | 1 | 35000 | Remove from Pvt Company hire list
4 | 1 | AVM | Manager, AV Caserta (AVC) | 1 | [6 empty] | 1 |  |  | IFEL | Voda |  | 5000 | 2019-03-04 | 2019-08-30 | 0.48889 | #REF! | M. Perotti | 179 | 7 | 1 | 35000 | Remove from Pvt Company hire list
5 | 1 | AVM | Manager, Arrivals & Departures (and DWC) | 1 | [6 empty] | 1 |  |  | IFEL | Voda |  | 5000 | 2019-03-04 | 2019-08-30 | 0.48889 | #REF! | S. Gabrielli | 179 | 7 | 1 | 35000 | Remove from Pvt Company hire list
6 | 1 | AVM | Asst Manager, AV Ops & Services (AVN) |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  | 4500 | 2019-03-18 | 2019-08-15 | 0.40833 | #REF! |  | 150 | 6 | 6 | 162000 | Change 18 open AVM positions to 13 and re-title
7 | 1 | AVM | Asst Manager, AV Ops & Services (AVN) |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  |  | 2019-03-18 | 2019-08-15
8 | 1 | AVM | Asst Manager, AV Ops & Services (AVS) |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  |  | 2019-03-18 | 2019-08-15
9 | 1 | AVM | Asst Manager, AV Ops & Services (AVC1/2/3) |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  |  | 2019-03-18 | 2019-08-15
10 | 1 | AVM | Asst Manager, AV Ops & Services (AVC4) |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  |  | 2019-03-18 | 2019-08-15
11 | 1 | AVM | Coordinator, AV Staffing, Training & Info |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 5 | 1 | 17500
12 | 1 | AVM | Coordinator, AV Ops & Services (AVN) |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  |  | 2019-04-01 | 2019-07-31
13 | 1 | AVM | Coordinator, AV Ops & Services (AVN) |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  |  | 2019-04-01 | 2019-07-31
14 | 1 | AVM | Coordinator, AV Ops & Services (AVS) |  |  | 1 | [5 empty] | 1 |  | 1 | 1 |  | 4500 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 6 | 1 | 27000
15 | 1 | AVM | Coordinator, AV Ops & Services (AVC 1/2/3/4) |  |  | 1 | [5 empty] | 1 |  | 1 | 1 |  | 3500 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 5 | 3 | 52500
16 | 1 | AVM | Coordinator, Guest Passes & Resident Services |  |  | 1 | [5 empty] | 1 |  | 1 | 1 |  | 3500 | 2019-04-15 | 2019-07-31 | 0.29444 | #REF! |  | 107 | 5 | 1 | 17500
17 | 1 | AVM | Coordinator, Arrivals & Departures (and DWC) |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  | 1 |  | 3500 | 2019-04-15 | 2019-07-31 | 0.29444 | #REF! |  | 107 | 5 | 2 | 35000 | Dupe
18 | 1 | AVM | Coordinator, Arrivals & Departures (and DWC) |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  |  | 2019-04-15 | 2019-07-31 | 0.29444 |  |  | 107
19 | 1 | AVM | Assistant, Arrivals & Departures |  |  |  |  | 1 | [9 empty] | 2019-06-10 | 2019-07-16 | 0.1 |  |  | 36
20 | 1 | AVM | Assistant, Arrivals & Departures |  |  |  |  | 1 | [9 empty] | 2019-06-10 | 2019-07-16
21 | 1 | AVM | Assistant, Arrivals & Departures |  |  |  |  | 1 | [9 empty] | 2019-06-10 | 2019-07-16
22 | 1 | AVM | Assistant, Arrivals & Departures |  |  |  |  | 1 | [9 empty] | 2019-06-10 | 2019-07-16
23 | 48 | AVM | Athletes Village/DWC Attendant |  |  |  |  | 48 |  |  | - | - | - | - | - |  | 2500 | 2019-06-17 | 2019-07-16 | 0.080556 | #REF! |  | 29 | 1 | 50 | 125000
|  |  | Sub total | 5 | 0 | 13 | 1 | 52 | 0 | 1290 | 13 | 5 | 3 | 10 | 13 | [5 empty] | #REF!
Ship Management/Crew | [9 empty] | 1000 | [11 empty] | 2 Ships
Dorm Housekeeping/Laundry Crew | [9 empty] | 200
Retail Services Crew | [9 empty] | 40 | [11 empty] | Various retail companies
Religious Services Crew | [9 empty] | 50 | [11 empty] | Religious entity
1 | 1 | BIL | Head of Brand, Identity & Look | 1 | [6 empty] | 1 |  |  | Existing | Existing |  | 6000 | 2018-05-15 | 2019-08-30 | 1.2917 | #REF! | V. Rosso
2 | 1 | BIL | Manager, Branding |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 4000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 7 | 1 | 28000
|  |  | Sub total | 1 | 0 | 1 | 0 | 0 | 0 | 111 | 2 | 0 | 1 | 0 | 1 | [5 empty] | #REF!
Manager, Design | [9 empty] | 1 | [11 empty] | Branding tender? GB to confirm
Senior Graphic Designer | [9 empty] | 1 | [11 empty] | Branding tender? GB to confirm
Graphic Designer | [9 empty] | 1 | [11 empty] | Branding tender? GB to confirm
Senior Venue Look Manager | [9 empty] | 4 | [11 empty] | Branding tender? GB to confirm
Production Coordinator | [9 empty] | 1 | [11 empty] | Branding tender? GB to confirm
Production Assistant | [9 empty] | 3 | [11 empty] | Branding tender? GB to confirm
Look Crew | [9 empty] | 100 | [11 empty] | Branding tender? GB to confirm
1 | 1 | CER | Head of Ceremonies | 1 | [6 empty] | 1 |  |  | IFEL | Voda |  | 6000 | 2019-03-04 | 2019-08-30 | 0.48889 | #REF! | C. Cennamo
2 | 1 | CER | Coordinator, Ceremonies |  |  |  | 1 |  |  |  | 1 |  |  | 1 | 1 |  | 3500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 7 | 1 | 24500
3 | 1 | CER | Manager, Torch Relay e culture education |  |  |  | 1 |  |  |  | 1 |  |  | 1 | 1 |  | 4000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 7 | 1 | 28000
4 | 1 | CER | Coordinator, Torch Relay |  |  |  | 1 |  |  |  | 1 |  |  | 1 | 1 |  | 3500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 5 | 1 | 17500
5 | 1 | CER | Coordinator, Culture and Education |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 3500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 5 | 1 | 17500
|  |  | Sub total | 1 | 0 | 0 | 4 | 0 | 0 | 300 | 5 | 0 | 1 | 3 | 4 | [5 empty] | #REF!
Ceremonies Mgt/Crew (not 'Cast') | [9 empty] | 300 | [11 empty] | Ceremonies company
1 | 1 | COM | Head of Communications |  |  |  | 1 |  |  |  | 1 |  |  | IFEL | Voda |  | 6000 | 2019-03-11 | 2019-09-30 | 0.55278 | #REF! |  | 203 | 8 | 1 | 48000 | In a tender? GB to confirm
2 | 1 | COM | Manager, Digital Strategy, PR & Promotion |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 4000 | 2019-03-11 | 2019-08-30 | 0.46944 | #REF! |  | 172 | 7 | 1 | 28000 | In a tender? GB to confirm
3 | 1 | COM | Coord, Social Media Engagement/Content | 1 | [6 empty] | 1 |  |  | IFEL | 1 |  | 3500 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! | F. Pison | 142 | 6 | 2 | 42000
4 | 1 | COM | Communications Assistant | 1 | [6 empty] | 1 |  |  | IFEL |  |  |  | add | 2019-07-31 |  |  | A. Bartoli
5 | 1 | COM | Photographer/Videographer |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 4 | 2 | 24000 | In a tender? GB to confirm
6 | 1 | COM | Journalist | 1 | [6 empty] | 1 |  |  | IFEL | 1 |  | 3000 | 2019-02-25 | 2019-07-31 | 0.43333 | 0 | F. Parrella
7 | 1 | COM | Journalist | 1 | [6 empty] | 1 |  |  | IFEL | 1 |  |  | 2019-02-25 | 2019-07-31 |  |  | C. Celli
8 | 1 | COM | Journalist |  | 1 | [5 empty] | 1 |  |  | IFEL | 1
|  |  | Sub total | 4 | 1 | 0 | 3 | 0 | 0 | 0 | 8 | 0 | 2 | 0 | 6 | [5 empty] | #REF!
1 | 1 | DEL | Head of Delegation Services | 1 | [6 empty] | 1 |  |  | Existing | Existing |  | 6000 | 2018-05-15 | 2019-08-30 | 1.2917 | #REF! | F. Cirianni
2 | 1 | DEL | Coordinator, Delegation Services | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-01-14 | 2019-08-16 | 0.58889 | #REF! | F. Di Nunno
3 | 1 | DEL | Coordinator, Delegation Services | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-01-14 | 2019-08-02 | 0.55 | #REF! | R. Lacerda Magalhaes
4 | 1 | DEL | Coordinator, Delegation Services | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-01-14 | 2019-08-02 | 0.55 | #REF! | M. Nazzaro
5 | 1 | DEL | Coordinator, Delegation Services | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-04 | 2019-08-02 | 0.41111 | #REF! | S. Petrone
6 | 1 | DEL | Coordinator, Delegation Services | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-04 | 2019-08-02 | 0.41111 | #REF! | G. Samartino
7 | 1 | DEL | Delegation Attache Supervisor |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF!
8 | 1 | DEL | Delegation Attache Supervisor |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  | 3000 | 2019-03-18 | 2019-07-31
9 | 1 | DEL | Delegation Service Center Supervisor |  |  |  |  | 1 | [8 empty] | 3000 | 2019-06-10 | 2019-07-16
10 | 1 | DEL | Delegation Service Center Supervisor |  |  |  |  | 1 | [8 empty] | 3000 | 2019-06-10 | 2019-07-16
11 | 1 | DEL | Delegation Service Center Supervisor |  |  |  |  | 1 | [8 empty] | 3000 | 2019-06-10 | 2019-07-16
12 | 1 | DEL | Delegation Service Center Supervisor |  |  |  |  | 1 | [8 empty] | 3000 | 2019-06-10 | 2019-07-16
13 | 1 | DEL | Delegation Service Center Supervisor |  |  |  |  | 1 | [8 empty] | 3000 | 2019-06-10 | 2019-07-16
14 | 1 | DEL | Delegation Service Center Supervisor |  |  |  |  | 1 | [8 empty] | 3000 | 2019-06-10 | 2019-07-16 | 0.1 | #REF! |  | 36 | 2 | 6 | 36000
15 | 220 | DEL | Delegation Attache |  |  |  |  | 220 | [8 empty] | 1500 | 2019-06-17 | 2019-07-16 | 0.080556 | #REF!
|  |  | Sub total | 6 | 0 | 2 | 0 | 226 | 0 |  | 6 | 2 | 2 | 0 | 7 | [5 empty] | #REF!
1 | 1 | FIN | Head of Finance and Administration | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | 6000 | 2019-01-14 | 2019-11-15 | 0.83611 | #REF! | [5 empty] | ask GB who fills this role
2 | 1 | FIN | Senior Accountant | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | 2019-01-28 | 2019-09-27 |  |  | G. Cianciulli
3 | 1 | FIN | Senior Accountant | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | 2019-01-28 | 2019-09-27 |  |  | A. Damiano
4 | 1 | FIN | Senior Accountant | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  | 3500 | 2019-01-28 | 2019-09-27 | 0.66389 | #REF! | A. Gemei
5 | 1 | FIN | Senior Accountant | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  | 3500 | 2019-02-04 | 2019-08-30 | 0.57222 | 0 | S. Restino
6 | 1 | FIN | Senior Accountant | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  |  | 2019-02-18 | 2019-08-30 |  |  | N. Della Corte
7 | 1 | FIN | Junior Accountant | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  |  | 2019-02-18 | 2019-08-30 |  |  | I. D'Ambro
8 | 1 | FIN | Junior Accountant | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  |  | 2019-02-18 | 2019-08-30 |  |  | L. Lucibelli
9 | 1 | FIN | Junior Accountant | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  |  | 2019-02-18 | 2019-08-30 |  |  | I. Iannella
10 | 1 | FIN | Junior Accountant | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  |  | 2019-02-18 | 2019-08-30 |  |  | A. Caso
11 | 1 | FIN | Junior Accountant | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  |  | 2019-02-18 | 2019-08-30 |  |  | F. Turco
12 | 1 | FIN | Coordinator, Legal, Tenders & Procurement | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  | 3500 | 2019-02-04 | 2019-08-16 | 0.53333 | 0 | R. Matarazzo
13 | 1 | FIN | Coordinator, Legal, Tenders & Procurement | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  | 3500 | 2019-02-18 | 2019-08-30 | 0.53333 | #REF! | G. Sestile
14 | 1 | FIN | Coordinator, Legal, Civil Sector | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  | 3500 | 2019-02-04 | 2019-08-30 | 0.57222 | #REF! | L. Muro
15 | 1 | FIN | Financial Consultant, Accounting | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | G. Raimondo
16 | 1 | FIN | Upfront Advisory, Accounting | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | C. Picardi
17 | 1 | FIN | Upfront Advisory, Accounting | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | L. Battiloro
18 | 1 | FIN | Upfront Advisory, Accounting | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | F. Esposito
19 | 1 | FIN | Commercial Consultant | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | V. Santis
20 | 1 | FIN | Auditor | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | P. Ricci
21 | 1 | FIN | Accounting Consultant | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | N. Petrellese
22 | 1 | FIN | Coordinator, Budget ('Audit') |  | 1 | [5 empty] | 1 |  | IFEL |  | Existing |  | 3500 | 2019-02-04 | 2019-08-16 | 0.53333 | 22400
23 | 1 | FIN | Coordinator, Budget ('Audit') |  | 1 | [5 empty] | 1 |  | IFEL |  | Existing |  | 3500 | 2019-02-04 | 2019-08-16 | 0.53333 | 22400
24 | 1 | FIN | Coordinator, Rate Card & VIK |  | 1 | [5 empty] | 1 |  | IFEL |  |  |  | 3500 | 2019-02-18 | 2019-08-30 | 0.53333 | #REF!
25 | 1 | FIN | Junior Accountant |  | 1 | [5 empty] | 1 |  | IFEL |  | Existing |  | 2500 | 2018-10-15 | 2019-08-30 | 0.875 | #REF!
26 | 1 | FIN | Junior Accountant |  | 1 | [5 empty] | 1 |  | IFEL |  | Existing |  | 2500 | 2019-01-28 | 2019-08-30 | 0.58889 | 17666.6667
27 | 1 | FIN | Specialist, Risk Management |  | 1 | [5 empty] | 1 |  | IFEL |  | Existing |  | 4000 | 2019-01-14 | 2019-08-16 | 0.58889 | #REF! | R. Grattocaso
Internal Auditor | [9 empty] | 3 | [11 empty] | Auditing company
Venue Safety Officer | [9 empty] | 6 | [11 empty] | Insurance company
Claims Specialist | [9 empty] | 6 | [11 empty] | Insurance company
28 | 1 | FIN | Commissioner | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  |  | 2016-09-01 | 2019-12-20 | 3.3028 |  | G. Basile
29 | 1 | FIN | General Coordinator, Games Delivery | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  |  | 2018-12-03 | 2019-10-25 | 0.89444 |  | A. Sotiriadis
30 | 1 | FIN | Director, Administration | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  |  | 2018-11-05 | 2019-12-20 | 1.125 |  | R. Fabiano
31 | 1 | FIN | Director, Institutional Relations | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  |  | 2016-10-15 | 2019-12-20 | 3.1806 |  | A. Voto
32 | 1 | FIN | Director, Marketing | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  |  | 2016-10-15 | 2019-09-27 | 2.95 |  | G. Candeloro
33 | 1 | FIN | Director, Games Services | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  | 8000 | 2019-02-01 | 2019-09-30 | 0.66389 | #REF! | C. Ubbiali | 241 | 8 | 1 | 64000 | Remove from Pvt Company hire list
34 | 1 | FIN | Director, Sport and Sport Services | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  |  | 2017-06-23 | 2019-12-20 | 2.4917 |  | R. Outeirino
35 | 1 | FIN | Director, Technology | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  |  | add | 2019-09-30 |  |  | S. Ferrandino
36 | 1 | FIN | Director, Venue Renovations | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  |  | 2016-10-15 | 2019-12-20 | 3.1806 |  | F. De Martino
37 | 1 | FIN | Assistant to Commissioner | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  |  | 2016-09-01 | 2019-12-20 | 3.3028 |  | S. Romano
38 | 1 | FIN | Assistant to General Coordinator | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | 3000 | 2019-02-01 | 2019-09-30 | 0.66389 | #REF! | E. Ligouri | 241 | 8 | 1 | 24000
39 | 1 | FIN | Assistant to Commissioner, Protocol | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | 2019-09-30 |  |  | G. Angrisano
40 | 1 | FIN | Assistant to Commissioner | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | 2019-09-30 |  |  | L. Ciarletta
41 | 1 | FIN | Assistant to Commissioner, Finance | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | 2019-09-30 |  |  | S. Colicchio
42 | 1 | FIN | Tenders consultant | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | T. Braucci
43 | 1 | FIN | Legal support | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | M.G. Cesaria
44 | 1 | FIN | Legal consultant | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | add |  |  | V. D'Anto
45 | 1 | FIN | Office Manager | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | 2019-09-30 |  |  | O. Ogliastro
46 | 1 | FIN | Office Assistant | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | add | 2019-09-30 |  |  | F. Ceglia
47 | 1 | FIN | Office Assistant |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  |  |  | 2019-03-18 | 2019-08-31 | 0.45278
48 | 1 | FIN | Office Assistant |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  |  | 2500 | 2019-03-25 | 2019-07-31 | 0.35 | #REF! |  | 128 | 8 | 1 | 20000
|  |  | Sub total | 40 | 6 | 2 | 0 | 0 | 0 | 15 | 48 | 0 | 2 | 0 | 0 | [5 empty] | #REF!
1 | 1 | FNB | Head of Food & Beverage | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 6000 | 2019-03-04 | 2019-08-31 | 0.49167 | #REF! | A. Cappiello
2 | 1 | FNB | Manager, Food & Bev Operations |  | 1 | [5 empty] | 1 |  | IFEL |  | 1 |  | 3500 | 2019-02-01 | 2019-07-31 | 0.5 | #REF! |  | 180 | 6 | 1 | 21000
3 | 1 | FNB | Coordinator, Food & Bev Administration |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3500 | 2019-02-01 | 2019-08-30 | 0.58056 | #REF! |  | 210 | 7 | 1 | 24500
4 | 1 | FNB | Coordinator, Athletes Village Food/Bev |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3500 | 2019-02-01 | 2019-07-31 | 0.5 | #REF! |  | 180 | 6 | 1 | 21000
|  |  | Sub total | 1 | 1 | 2 | 0 | 0 | 0 | 800 | 4 | 0 | 2 | 0 | 4 | [5 empty] | #REF!
Food and Beverage Supervisor/Crew | [9 empty] | 800 | [6 empty] | Contract | 2019-06-15 | 2019-07-19 | 0.094444 | 0 | Food services companies
1 | 1 | LOG | Head of Logistics |  | 1 | [5 empty] | 1 |  | IFEL |  | 1 |  | 6000 | 2019-01-15 | 2019-09-30 | 0.70833 | #REF! | M. Verger
2 | 1 | LOG | Manager, Venue Logistics |  |  | 1 |  |  |  |  | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-11 | 2019-08-30 | 0.46944 | #REF! | A. Ernano | 172 | 7 | 1 | 28000
3 | 1 | LOG | Manager, Material Logistics |  |  | 1 |  |  |  |  | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-04 | 2019-08-30 | 0.48889 | #REF! | R. Dughet | 179 | 6 | 1 | 24000
|  |  | Sub total | 0 | 1 | 2 | 0 | 0 | 0 | 273 | 3 | 0 | 0 | 0 | 3 | [5 empty] | #REF!
Manager, Supply Chain/Warehouse | [9 empty] | 1 | [11 empty] | Logistics company
Coordinator, Freight and Shipping | [9 empty] | 1 | [11 empty] | Logistics company
Material Planner | [9 empty] | 2 | [11 empty] | Logistics company
Inventory Control Clerk | [9 empty] | 2 | [11 empty] | Logistics company
Shipping & Receiving Clerk | [9 empty] | 2 | [11 empty] | Logistics company
Traffic Control & Dispatch Clerk | [9 empty] | 1 | [11 empty] | Logistics company
Warehouse Supervisor | [9 empty] | 4 | [11 empty] | Logistics company
Senior Venue Logistics Manager | [9 empty] | 4 | [11 empty] | Logistics company
Material Handler (Warehouse) | [9 empty] | 20 | [11 empty] | Logistics company
Material Handler (Venue/Warehouse) | [9 empty] | 236 | [11 empty] | Logistics company
1 | 1 | MAR | Head of Marketing and Licensing | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 6000 | 2019-02-25 | 2019-08-30 | 0.51389 | #REF! | D. Napoli
2 | 1 | MAR | Head of Ticketing | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 6000 | 2019-02-25 | 2019-08-30 |  |  | E. De Bury
3 | 1 | MAR | Manager, Marketing | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-02-25 | 2019-07-31 | 0.43333 | #REF! | E. Salzano
4 | 1 | MAR | Coordinator, Marketing | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 3500 | 2019-02-25 | 2019-07-31 | 0.43333 | #REF! | F. D'Anna (also Mascot)
5 | 1 | MAR | Coordinator, Licensing and Merchandising |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
6 | 1 | MAR | Coordinator, Ticket Operations |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
7 | 1 | MAR | Coordinator, Ticket Sales |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
8 | 1 | MAR | Coord, Ticketed Ceremonies/Spec Projects |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 6 | 1 | 18000
9 | 1 | MAR | Marketing Intern | 1 | [6 empty] | 1 |  | Existing |  |  |  |  | 2019-01-01 | 2019-07-16 | 0.54167 |  | A. Improta
10 | 1 | MAR | Marketing Intern | 1 | [6 empty] | 1 |  | Existing |  |  |  |  | 2019-01-01 | 2019-07-16 |  |  | R. Landolfi
11 | 1 | MAR | Marketing Intern | 1 | [6 empty] | 1 |  | Existing |  |  |  |  | 2019-01-01 | 2019-07-16 |  |  | R. Nicotra
|  |  | Sub total | 7 | 0 | 0 | 4 | 0 | 0 | 399 | 11 | 0 | 4 | 0 | 8 | [5 empty] | #REF!
Manager, Marketing Partner Sales | [9 empty] | 1 | [11 empty] | Marketing agency, if applic
Account Manager, Marketing Partners | [9 empty] | 2 | [11 empty] | Marketing agency, if applic
Coordinator, Marketing Partner Sales | [9 empty] | 1 | [11 empty] | Marketing agency, if applic
Merchandising Supervisor/Crew | [9 empty] | 255 | [11 empty] | Tender? Which one?
Box Office/Ticketing Systems Crew | [9 empty] | 140 | [11 empty] | Tender? Which one?
1 | 1 | MBS | Head of Media & Broadcast Services | 1 | [6 empty] | 1 |  | IFEL |  | Voda |  | 6000 | 2019-02-25 | 2019-09-13 | 0.55 | #REF! | A. Gnassi
2 | 1 | MBS | Manager, Media & Broadcast Services |  |  |  | 1 |  |  |  | 1 |  | Tender |  | Tender |  | 4000 | 2019-03-11 | 2019-08-31 | 0.47222 | #REF! |  | 173 | 6 | 1 | 24000 | RTS or HB tender?
3 | 1 | MBS | Coord, Venue Media & Broadcast Ops |  |  |  | 1 |  |  |  | 1 |  | Tender |  | Tender |  | 3500 | 2019-03-25 | 2019-07-31 | 0.35 | #REF! |  | 128 | 6 | 1 | 21000 | RTS or HB tender? Remove from Pvt Comp hire list?
4 | 1 | MBS | MPC Manager |  |  |  | 1 |  |  |  | 1 |  | Tender |  | Tender |  | 3000 | 2019-05-06 | 2019-07-31 | 0.23611 | #REF! |  | 86 | 3 | 1 | 9000 | RTS or HB tender? Remove from Pvt Comp hire list?
5 | 1 | MBS | MPC Coordinator |  |  |  | 1 |  |  |  | 1 |  | Tender |  | Tender |  | 2500 | 2019-06-03 | 2019-07-31 | 0.16111 | #REF! |  | 58 | 2 | 2 | 10000 | RTS or HB tender?
6 | 1 | MBS | MPC Coordinator |  |  |  | 1 | [5 empty] | Tender |  | Tender |  |  | 2019-06-03 | 2019-07-31 | [7 empty] | RTS or HB tender?
7 | 20 | MBS | Media and Broadcast Services Supervisor |  |  |  | 1 | [5 empty] | Tender |  | Tender |  | 2000 | 2019-06-15 | 2019-07-15 | 0.083333 | #REF! |  | 30 | 1 | 18 | 36000 | RTS or HB tender?
|  |  | Sub total | 1 | 0 | 0 | 6 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | [5 empty] | #REF!
1 | 1 | MED | Chief Medical & Doping Control Officer | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  | 0 | 2018-09-15 | 2019-08-30 | 0.95833 | 0 | A. De Paulis
2 | 1 | MED | Head of Medical Services & Doping Control | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | 6000 | 2019-02-01 | 2019-09-30 | 0.66389 | #REF! | B. Liccardo | 241 | 7 | 1
3 | 1 | MED | Manager, Medical Services Naples | 1 | [6 empty] | 1 |  | Tender |  | Tender |  | 6000 | 2019-02-01 | 2019-07-31 | 0.5 | #REF! |  | 180 | 6 | 1 | 36000 | Ask Bianca for name
4 | 1 | MED | Manager, Medical Services Salerno | 1 | [6 empty] | 1 |  | Tender |  | Tender |  | 6000 | 2019-02-01 | 2019-07-31 | 0.5 | #REF! |  | 180 | 6 | 1 | 36000 | Ask Bianca for name
5 | 1 | MED | Manager, Medical Services Caserta | 1 | [8 empty] | Tender |  | Tender |  | 6000 | 2019-02-01 | 2019-07-31 | 0.5 | #REF! |  | 180 | 6 | 1 | 36000 | Ask Bianca for name
6 | 2 | MED | Coordinator, Med & DC Staffing/Training |  |  |  | 1 |  |  |  | 1 |  | Tender |  | Tender |  | 4000 | 2019-03-11 | 2019-07-16 | 0.34722 | #REF! |  | 127 | 6 | 2 | 48000
7 | 2 | MED | Medical Services Administrator |  |  |  | 1 |  |  |  | 1 |  | Tender |  | Tender |  | 3000 | 2019-04-01 | 2019-07-16 | 0.29167 | #REF! |  | 106 | 3 | 2 | 18000
|  |  | Sub total | 5 | 0 | 0 | 2 | 0 | 0 | 328 | 6 | 0 | 0 | 0 | 0 | [5 empty] | #REF!
Advisor, Medical Services & Doping Control | [9 empty] | 1 | [9 empty] | 0 | 0 | V. Caputo
Coord, Doping Control Operations | [9 empty] | 1 | [11 empty] | FIMS provides
Coord, Doping Control Admin | [9 empty] | 1 | [11 empty] | FIMS provides
Venue Medical & Doping Control Mgr | [9 empty] | 24 | [11 empty] | Service Provider
Doping Control Officer | [9 empty] | 24 | [11 empty] | FIMS provides
Lab Courier | [9 empty] | 30 | [11 empty] | Courier company
Ambulance Driver | [9 empty] | 248 |  | 0 | [9 empty] | Ambulance company
1 | 1 | PC4 | Head of Planning & C4 | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 6000 | 2019-01-14 | 2019-09-13 | 0.66389 | #REF! | C. Capponi
2 | 1 | PC4 | Manager, Planning & C4 |  | 1 | [5 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-11 | 2019-08-30 | 0.46944 | #REF! |  | 172 | 6 | 1 | 24000
3 | 1 | PC4 | Coordinator, Planning & C4 |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 6 | 1 | 18000
|  |  | Sub total | 1 | 1 | 1 | 0 | 0 | 0 |  | 3 | 0 | 1 | 0 | 3 | [5 empty] | #REF!
1 | 1 | PFR | Head of Protocol & FISU Relations | 1 | [6 empty] | 1 |  |  | IFEL | 1 |  | 6000 | 2019-03-04 | 2019-09-13 | 0.525 | #REF! | F. De Rosa (also ROY Mgr) | 193 | 8 | 1 | 48000
2 | 1 | PFR | Manager, Protocol & FISU Relations | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-04 | 2019-08-30 | 0.48889 | #REF! | I. Shevcuk
3 | 1 | PFR | Manager, Lang Svcs, KM, Observer Program | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-02-11 | 2019-08-30 | 0.55278 | #REF! | G. M. Donadio
4 | 1 | PFR | Manager, Accommodations | 1 | [6 empty] | 1 |  | Existing |  | Existing |  |  | 2019-02-11 | 2019-08-30 | 0.55278 |  | V. Smeriglia
5 | 1 | PFR | Coordinator, Special Events |  |  |  | 1 |  |  |  | 1 |  |  | Tender | Tender |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
6 | 1 | PFR | Coordinator, FISU Family Attaches |  |  |  | 1 |  |  |  | 1 |  |  | Tender | Tender |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
7 | 1 | PFR | Coordinator, Lang Svcs, KM, Observer Prog |  |  |  | 1 |  |  |  | 1 |  |  | Tender | Tender |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
8 | 1 | PFR | Coordinator, Protocol & FISU Relations |  |  |  | 1 |  |  |  | 1 |  |  | Tender | Tender |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 7 | 1 | 21000
9 | 1 | PFR | Coordinator, PFR Staffing |  |  |  | 1 |  |  |  | 1 |  |  | Tender | Tender |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
10 | 1 | PFR | Assistant, Protocol & FISU Relations Admin | [7 empty] | 1 |  | Existing |  | Existing |  |  | add | 2019-09-30 |  |  | V. Sicurenza
11 | 1 | PFR | Assistant, Protocol & FISU Relations | [7 empty] | 1 |  | Existing |  |  |  | 2500 | 2019-04-15 | 2019-07-31 | 0.29444 | #REF! | C. Moriello (to confirm) | 107 | 5 | 4 | 50000
12 | 1 | PFR | Assistant, Protocol & FISU Relations | [7 empty] | 1 |  | Existing |  |  |  |  | 2019-04-15 | 2019-07-31 | 0.29444 |  | M. Vitale (to confirm) | 107
13 | 1 | PFR | Assistant, Protocol & FISU Relations | [7 empty] | 1 |  | Existing |  |  |  |  | 2019-04-15 | 2019-07-31 |  |  | P. Del Giudice (to confirm)
14 | 1 | PFR | Assistant, Protocol & FISU Relations | [7 empty] | 1 |  | Existing |  |  |  |  | 2019-04-15 | 2019-07-31 |  |  | M. Falsetto (to confirm)
15 | 1 | PFR | Protocol & FISU Relations Intern | [7 empty] | 1 |  | Existing |  |  |  |  | add | 2019-07-31 |  |  | F. Petrucci
16 | 1 | PFR | Protocol & FISU Relations Intern | [7 empty] | 1 |  | Existing |  |  |  |  | add | 2019-07-31 |  |  | C. Ruocco
|  |  | Sub total | 4 | 0 | 0 | 5 | 0 | 0 | 1216 | 16 | 0 | 0 | 0 | 3 | [5 empty] | #REF!
Mgr, Accommodations | [9 empty] | 1 | 1 | [10 empty] | Cisalpina (L Camareno)
Simultaneous Interpreter/Technician | [9 empty] | 15 | [6 empty] | 1906-11-04 |  |  |  |  | Lang Services company | 0 | 1 | 15 | 37500
Accommodations Mgt/Crew | [9 empty] | 1200 | 17 | 0 | [9 empty] | Various hotels
1 | 1 | SEI | Head of Security Integration | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 6000 | 2019-01-14 | 2019-09-13 | 0.66389 | #REF! | L. Zanoni
2 | 1 | SEI | Manager, Security Integration |  | 1 | [5 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 24000 | Remove from Pvt Company hire list
|  |  | Sub total | 1 | 1 | 0 | 0 | 0 | 0 | 2148 | 2 | 0 | 0 | 0 | 2 | [5 empty] | #REF!
| Security Integration Liaison | [8 empty] | 1 | 1
| Venue Security Manager | [8 empty] | 35
| Deputy Venue Security Manager | [8 empty] | 12
| Fire Supervisor/Officer | [8 empty] | 100
| Police/Military Supervisor/Officer | [8 empty] | 500
| Security Supervisor/Officer | [8 empty] | 1500 | 3 | 0
1 | 1 | SPT | Head of Sport |  | 1 | [5 empty] | 1 |  |  | IFEL | Voda |  | 6000 | 2019-03-11 | 2019-09-30 | 0.55278 | #REF! |  | 203 | 7 | 1 | 42000
2 | 1 | SPT | Manager, Sport Services | 1 | [6 empty] | 1 |  |  | Existing | Existing |  |  | add | 2019-10-25 |  |  | S. Marzullo
3 | 1 | SPT | Manager, Sport Operations |  | 1 | [5 empty] | 1 |  |  | IFEL | 1 |  | 4000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 24000 | Remove from Pvt Company hire list
4 | 1 | SPT | Manager, Awards & Sport Presentation |  | 1 | [5 empty] | 1 |  |  | IFEL | 1 |  | 4000 | 2019-03-11 | 2019-09-13 | 0.50556 | #REF!
5 | 1 | SPT | Coordinator, Training Sites |  | 1 | [5 empty] | 1 |  |  | IFEL | 1 |  | 3500 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 21000 | Remove from Pvt Company hire list
6 | 1 | SPT | Manager, Sport Entries & RTS | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-04 | 2019-09-13 | 0.525 | #REF! | A. Iommi
7 | 1 | SPT | Coordinator, Sports Equipment | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 3500 | add | 2019-07-31 | #VALUE! | #VALUE! | M. Di Roucco | #VALUE! | 6 | 1 | 21000 | Remove from Pvt Company hire list
8 | 1 | SPT | Coordinator, ITO/NTO Services | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 3500 | 2019-03-04 | 2019-07-31 | 0.40833 | #REF! | A. Giuliani | 149 | 6 | 1 | 21000 | Remove from Pvt Company hire list
9 | 1 | SPT | Coord, Sport Publications & Information | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 3500 | 2019-03-04 | 2019-07-31 | 0.40833 | #REF! | A. Del Gaudio | 149 | 6 | 1 | 21000 | Remove from Pvt Company hire list
10 | 1 | SPT | Coord, Sport Publications & Information | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 3500 | 2019-03-04 | 2019-07-31 | 0.40833 | #REF! | M. Lapore | 149 | 6 | 1 | 21000
11 | 1 | SPT | Coord, Awards & Sport Presentation |  |  | 1 | 1 |  |  |  | 1 |  | 1 |  | 2 |  | 3500 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 2 | 42000 | In RTS tender? Dupe? Remove from Pvt Comp hire list?
12 | 1 | SPT | Coord, Awards & Sport Presentation |  |  | 1 | 1 |  |  |  | 1 |  | 1 |  | 2 |  | 3500 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 2 | 42000 | In RTS tender? Dupe? Remove from Pvt Comp hire list?
13 | 1 | SPT | Coord, Sport Staffing |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 21000
14 | 1 | SPT | Assistant, Sport |  |  | 1 | [5 empty] | 1 | 1 |  | 2 |  | 2500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 5 | 2 | 25000 | Remove 1 from Pvt Comp list
15 | 1 | SPT | Assistant, Training Sites |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 2500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 5 | 1 | 12500
16 | 1 | SPT | Assistant, Sport Entries | 1 | [6 empty] | 1 |  | 1 |  | 2 |  | 2500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! | M. Renna (to confirm) | 135 | 5 | 2 | 25000 | Remove 2 from pvt comp list
17 | 1 | SPT | Assistant, ITO Services | 1 | [7 empty] | 1 | 1 |  | 1 |  | 2500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! | D. Iaco (to confirm) | 135 | 5 | 1 | 12500 | Remove 1 from pvt comp list
18 | 25 | SPT | Sport Information Supervisor |  |  |  |  | 25 |  |  |  |  | Planned |  | 25 |  | 1500 | 2019-06-03 | 2019-07-16 | 0.11944 | 53750 |  | 43 | 2 | 18 | 54000
19 | 124 | SPT | Team Liaison |  |  |  |  | 124 | [6 empty] | 124 |  |  | 2019-06-17 | 2019-07-15 |  | Count as 'C' not 'P'
|  |  | Sub total | 8 | 4 | 5 | 2 | 149 | 0 | 243 | 15 | 20 | 7 | 0 | 168 | [5 empty] | #REF!
Competition Manager | [9 empty] | 18 |  | 18 | [9 empty] | Per NSFs
Sport Venue Coordinator | [9 empty] | 26 | [6 empty] | 1906-11-04 |  |  |  |  | Per NSFs | 0 | 1 | 32 | 80000 | Included in NSF Agreements?
Field of Play Coordinator | [9 empty] | 16 | [6 empty] | 1906-11-04 |  |  |  |  | Per NSFs | 0 | 1 | 22 | 55000
Training Site Coordinator | [9 empty] | 28 | [6 empty] | 1906-11-04 |  |  |  |  | Per NSFs | 0 | 1 | 27 | 67500
Venue Awards & Sports Presentation Manager | [9 empty] | 18 | [6 empty] | 1906-11-04 |  |  |  |  | In SP agreement | 0 | 1 | 17 | 42500
Announcer | [9 empty] | 60 | [11 empty] | Per NSFs, in SP agreement
Sports Equipment Supplier | [9 empty] | 22 | [6 empty] | 1906-11-04 |  |  |  |  | In SP agreement | 0 | 1 | 18 | 45000
Lifeguard | [9 empty] | 16 | [6 empty] | 1906-11-04 |  |  |  |  | In SP agreement | 0 | 1 | 20 | 50000
Audio/Video Technician | [9 empty] | 39 | [11 empty] | In SP agreement
1 | 1 | TEC | Head of Technology | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  | 6000 | 2019-03-04 | 2019-10-25 | 0.64167 | #REF! | E. Dias
2 | 1 | TEC | Manager, Venue Technology | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-01-14 | 2019-09-13 | 0.66389 | #REF! | N. Zanfardino
3 | 1 | TEC | Manager, Corporate IT & Service Delivery | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-01-14 | 2019-09-27 | 0.70278 | #REF! | L. D'Angelo
4 | 1 | TEC | Coordinator, Technology Infrastructure | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 3500 | 2019-02-18 | 2019-08-16 | 0.49444 | #REF! | G. P. Sepe
5 | 1 | TEC | Manager, Games Mgt Systems (GMS) |  |  |  | 1 |  |  |  | 1 |  |  | Tender | 1 |  | 4000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! | In RTS tender? | 142 | 6 | 1 | 24000
6 | 1 | TEC | Coordinator, Office Technology | 1 | [6 empty] | 1 |  | Existing |  | 1 |  | 3500 | 2019-01-14 | 2019-09-27 | 0.70278 | #REF! | Vito?
7 | 1 | TEC | Technology Infrastructure Specialist |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF!
8 | 1 | TEC | Coordinator, Wifi Operations |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3500 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 21000
9 | 1 | TEC | Coordinator, TOC and Help Desk |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3500 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 6 | 1 | 21000
10 | 1 | TEC | Office Technology Specialist | 1 | [6 empty] | 1 |  | Existing |  | 2 |  | 3000 | 2019-02-01 | 2019-07-31 | 0.5 | #REF! | Luca? | 180 | 6 | 2 | 36000
11 | 1 | TEC | Office Technology Specialist | 1 | [6 empty] | 1 |  | 1 |  | 2 |  | 3000 | 2019-02-01 | 2019-07-31 | 0.5 | #REF! | add, already hired? | 180 | 6 | 2 | 36000
12 | 35 | TEC | Venue Technology Manager |  |  |  |  | 35 |  |  |  | 35 |  | Tender | 35 |  | 2500 | 2019-05-06 | 2019-07-31 | 0.23611 | 247916.6667 | Or in a tender? | 86 | 3 | 31 | 232500
|  |  | Sub total | 7 | 0 | 3 | 1 | 35 | 0 | 251 | 11 | 35 | 4 | 0 | 47 | [5 empty] | #REF!
Senior Technology Advisor | [9 empty] | 1 | 1 | [10 empty] | M Bisogno
Manager, Timing, Scoring & Results | [9 empty] | 1 | [11 empty] | Service Provider RTS
Manager, Telecommunications | [9 empty] | 1 | [11 empty] | Service Provider TELE
Coordinator, Timing, Scoring & Results | [9 empty] | 1 | 1 | [10 empty] | Service Provider RTS
Coordinator, Telecommunications | [9 empty] | 1 | [11 empty] | Service Provider TELE
Timing, Scoring & Results Crew | [9 empty] | 146 | [11 empty] | Service Provider RTS
Telecom Crew | [9 empty] | 100 | 13 | 35 | [9 empty] | Service Provider TELE
1 | 1 | TRA | Head of Transportation | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  | 6000 | 2018-05-15 | 2019-09-15 | 1.3333 | #REF! | M. Gambuto
2 | 1 | TRA | Co-Head of Transportation | 1 | [6 empty] | 1 |  | Existing | Existing | Existing |  | 6000 | 2018-12-03 | 2019-09-15 |  |  | A. Ramaglia
3 | 1 | TRA | Manager, Fleet Operations |  | 1 | [5 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-11 | 2019-09-13 | 0.50556 | #REF!
4 | 1 | TRA | Manager, Venue Transportation Operations |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 4000 | 2019-03-11 | 2019-08-02 | 0.39167 | #REF!
5 | 1 | TRA | Manager, Bus Operations |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 4000 | 2019-03-11 | 2019-08-02 | 0.39167 | #REF!
6 | 1 | TRA | Coordinator, Delegation Bus Operations |  | 1 | [5 empty] | 1 |  | IFEL |  | 1 |  | 3000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 18000 | Remove from Pvt Comp list
7 | 1 | TRA | Coordinator, ITO & Media Fleet/Bus Ops |  | 1 | [5 empty] | 1 |  | IFEL |  | 1 |  | 3000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 18000 | Remove from Pvt Comp list
8 | 1 | TRA | Coordinator, Fleet Ops/Motorpool |  | 1 | [5 empty] | 1 |  |  | IFEL | 1 |  | 3000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 18000 | Remove from Pvt Comp list
9 | 1 | TRA | Coordinator, Venue Transport Ops |  | 1 | [5 empty] | 1 |  |  | IFEL | 1 |  | 3000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 18000 | Remove from Pvt Comp list
10 | 1 | TRA | Coordinator, Mapping |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  |  | 3000 | 2019-03-18 | 2019-07-31
11 | 1 | TRA | Coordinator, Parking & Permits |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 6 | 1 | 18000
12 | 1 | TRA | Coordinator, Arrivals & Departures |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  | 3000 | 2019-04-15 | 2019-07-31 | 0.29444 | #REF! |  | 107 | 6 | 1 | 18000
13 | 1 | TRA | Coordinator, Transport Staffing |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 18000
14 | 1 | TRA | Coordinator, Transport Special Projects |  |  | 1 |  |  |  |  | 1 |  | Existing |  | Existing |  | 3000 | 2019-04-15 | 2019-07-31 | 0.29444 | #REF! | G. Pezzella (to confirm) | 107 | 5 | 1 | 15000 | If so, remove from Pvt comp list
15 | 1 | TRA | Sr. Venue Transport Manager |  |  | 1 | [5 empty] | 1 |  | 1 | 1 |  | 3000 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 4 | 4 | 48000
16 | 1 | TRA | Sr. Venue Transport Manager |  |  | 1 | [5 empty] | 1 |  | 1 | 1 |  | 3000 | 2019-04-01 | 2019-07-31
17 | 1 | TRA | Sr. Venue Transport Manager |  |  | 1 | [5 empty] | 1 |  | 1 | 1 |  | 3000 | 2019-04-01 | 2019-07-31
18 | 1 | TRA | Sr. Venue Transport Manager |  |  | 1 | [5 empty] | 1 |  | 1 | 1 |  | 3000 | 2019-04-01 | 2019-07-31
19 | 1 | TRA | Assistant, Parking & Permits |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  | 2000 | 2019-05-06 | 2019-07-16 | 0.19444 | #REF! |  | 71 | 4 | 1 | 8000
20 | 1 | TRA | Assistant, Arrivals & Departures |  |  |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 2000 | 2019-06-03 | 2019-07-16 | 0.11944 | #REF! |  | 43 | 2 | 3 | 12000
21 | 1 | TRA | Assistant, Arrivals & Departures |  |  |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 2000 | 2019-06-03 | 2019-07-16
22 | 1 | TRA | Assistant, Arrivals & Departures |  |  |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 2000 | 2019-06-03 | 2019-07-16
23 | 1 | TRA | Assistant, T1/T2/T3 Fleet |  |  |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 2000 | 2019-06-03 | 2019-07-16 | 0.11944 | #REF! |  | 43 | 2 | 3 | 12000
24 | 1 | TRA | Assistant, T1/T2/T3 Fleet |  |  |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 2000 | 2019-06-03 | 2019-07-16
25 | 1 | TRA | Assistant, ITO & Media Fleet/Bus Ops |  |  |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 2000 | 2019-06-03 | 2019-07-16 | 0.11944 | #REF! |  | 43 | 2 | 1 | 4000
|  |  | Sub total | 2 | 5 | 12 | 0 | 6 | 0 | 2244 | 14 | 5 | 12 | 5 | 21 | [5 empty] | #REF!
Manager, Public Transport & Traffic | [9 empty] | 1 | [11 empty] | Arcamir
Limo/Taxi Dispatcher/Supervisor | [9 empty] | 15 | [11 empty] | Limo service/taxi co
Limo/Taxi Driver | [9 empty] | 1000 | [11 empty] | Limo service/taxi co
Bus Dispatcher/Supervisor | [9 empty] | 25 | [11 empty] | Bus company
Bus Scheduler (Dispatcher) | [9 empty] | 3 | [11 empty] | Bus company
Bus Driver | [9 empty] | 600 | [11 empty] | Bus company
Parking Supervisor/Attendant | [9 empty] | 400 | [11 empty] | Parking company(ies)
Traffic Control Sprvr/Attendant | [9 empty] | 200 | [11 empty] | Public authority
1 | 1 | VEI | Head of Venues & Infrastructure | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | 6000 | add | 2019-09-30 | #VALUE! | #VALUE! | P. Delle Donne
2 | 1 | VEI | Manager, Venues & Infrastructure | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-09-30 |  |  | G. Notarnicola
3 | 1 | VEI | Functional Architect | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | G. Acampora
4 | 1 | VEI | Functional Architect | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | S. Fontana
5 | 1 | VEI | Functional Architect | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | G. Langella
6 | 1 | VEI | Functional Architect | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | F. Smiraglia
7 | 1 | VEI | Architect | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | G. Izzo
8 | 1 | VEI | Architect | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | D. Peluso
9 | 1 | VEI | Technical Architect | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | M. Pipolo
10 | 1 | VEI | V&I Consultant | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | M. Buonocore
11 | 1 | VEI | V&I Technical area (Benevento) | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | U. Dell'Omo
12 | 1 | VEI | V&I Infrastructure | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | A. Gloria
13 | 1 | VEI | V&I Infrastructure | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | A. Martone
14 | 1 | VEI | V&I Administrative Director | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | M. Di Lauro
15 | 1 | VEI | V&I Administrative Instructor | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-09-30 |  |  | G. Vaccaro
16 | 1 | VEI | V&I Administrative Instructor | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | C. Montella
17 | 1 | VEI | V&I Administrative Support | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | add | add | 2019-07-31 |  |  | R. Rizzo
18 | 1 | VEI | Sr. Civil Engineer | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 | 0.66389 | 0 | M. Mirabella
19 | 1 | VEI | Sr. Civil Engineer | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 |  |  | L. Pianese
20 | 1 | VEI | Sr. Civil Engineer | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 |  |  | G. Polito
21 | 1 | VEI | Sr. Civil Engineer | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 |  |  | T. Massimo
22 | 1 | VEI | Jr. Civil Engineer | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 | 0.66389 | 0 | C. Borrelli
23 | 1 | VEI | Jr. Civil Engineer | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 |  |  | A. De Sarno Prignano
24 | 1 | VEI | Jr. Civil Engineer | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 |  |  | A. Napoli
25 | 1 | VEI | Jr. Civil Engineer | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 |  |  | A. Sasso
26 | 1 | VEI | Jr. Civil Engineer | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 |  |  | D. Vitiello
27 | 1 | VEI | Safety Specialist | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 | 0.66389 | 0 | G. Fragiacomo
28 | 1 | VEI | Safety Specialist | 1 | [6 empty] | 1 |  | IFEL |  |  |  | 4000 | 2019-01-14 | 2019-09-13 | 0.66389 | #REF! | L. Leone | 242 | 7 | 4 | 112000
29 | 1 | VEI | Safety Specialist | 1 | [6 empty] | 1 |  | IFEL |  |  |  |  | 2019-01-14 | 2019-09-13 |  |  | G. Sessa
30 | 1 | VEI | Coordinator, Energy/Power/Electrical |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  | 3000 | 2019-03-04 | 2019-07-31 | 0.40833 | #REF! | G. Gentile | 149 | 6 | 1 | 18000
31 | 1 | VEI | Overlay Designer |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  |  | 3000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 18000
32 | 1 | VEI | CAD Specialist |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  |  | 3000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 18000
|  |  | Sub total | 29 | 1 | 2 | 0 | 0 | 0 | 502 | 32 | 0 | 3 | 0 | 1 | [5 empty] | #VALUE!
Overlay and Installation Consultant | [9 empty] | 2 | [11 empty] | CONI Servizi
Maintenance Crew | [9 empty] | 500 | [11 empty] | Existing venue workforce
1 | 1 | VEM | Head of Venue Management | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  | 6000 | 2019-01-14 | 2019-09-13 | 0.66389 | #REF! | V. M. Genovese
2 | 1 | VEM | Manager, Venue Management | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  | 4000 | 2019-01-14 | 2019-09-13 | 0.66389 | #REF! | F. Furno
3 | 1 | VEM | Manager, Event Services & Signage Prog | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  | 4000 | 2019-03-04 | 2019-08-15 | 0.44722 | #REF! | S. Hallifax
4 | 1 | VEM | Manager, Overlay & Installations |  |  | 1 |  |  |  |  | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-11 | 2019-09-13 | 0.50556 | #REF!
5 | 1 | VEM | Manager, Event Communications |  |  | 1 |  |  |  |  | 1 |  | IFEL |  | 1 |  | 4000 | 2019-04-01 | 2019-08-15 | 0.37222 | #REF! |  | 136 | 7 | 1 | 28000
6 | 1 | VEM | Venue Projects Specialist | 1 | [6 empty] | 1 |  | IFEL |  | Existing |  |  | 2019-01-14 | 2019-07-31 | 0.54722 |  | B. Campanile
7 | 1 | VEM | Senior Venue Manager | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 3500 | 2019-03-04 | 2019-08-30 | 0.48889 | #REF! | F. Lombardese | 179 | 7 | 5 | 122500 | Remove from Pvt Comp list
8 | 1 | VEM | Senior Venue Manager | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  |  | 2019-03-04 | 2019-08-30 |  |  | G. Gennaro |  |  |  |  | Remove from Pvt Comp list
9 | 1 | VEM | Senior Venue Manager | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  |  | 2019-03-04 | 2019-08-30 |  |  | A. Roberti |  |  |  |  | Remove from Pvt Comp list
10 | 1 | VEM | Senior Venue Manager | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  |  | 2019-03-04 | 2019-08-30 |  |  | F. De Cicco |  |  |  |  | Remove from Pvt Comp list
11 | 1 | VEM | Senior Venue Manager | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  |  | 2019-03-04 | 2019-08-30 |  |  | G. Roca |  |  |  |  | Remove from Pvt Comp list
12 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  | 3500 | 2019-03-11 | 2019-08-30 | 0.46944 | #REF! | V. Incantalupo | 172 | 7 | 25 | 612500 | Remove from Pvt Comp list
13 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-11 | 2019-08-30 |  |  | A. Ciccone |  |  |  |  | Remove from Pvt Comp list
14 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-11 | 2019-08-30 |  |  | V. Rossi |  |  |  |  | Remove from Pvt Comp list
15 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-11 | 2019-08-30 |  |  | M. Diavino |  |  |  |  | Remove from Pvt Comp list
16 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-11 | 2019-08-30 |  |  | G. Casburi |  |  |  |  | Remove from Pvt Comp list
17 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-18 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
18 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-18 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
19 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-18 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
20 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-18 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
21 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-18 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
22 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-25 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
23 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  | 3500 | 2019-03-25 | 2019-08-15 | 0.38889 | #REF! |  | 143 | 7 | 25 | 612500 | Remove from Pvt Comp list
24 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-25 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
25 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-25 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
26 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-03-25 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
27 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-04-01 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
28 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-04-01 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
29 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-04-01 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
30 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-04-01 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
31 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-04-01 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
32 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-04-01 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
33 | 1 | VEM | Venue Manager |  | 1 | [6 empty] | 1 | IFEL |  | 1 |  |  | 2019-04-01 | 2019-08-15 | [7 empty] | Remove from Pvt Comp list
34 | 1 | VEM | Coordinator, Overlay and Installations | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! | A. Raffaele | 135 | 6 | 1 | 18000
35 | 1 | VEM | Coordinator, Venue Management |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
36 | 1 | VEM | Coordinator, Readiness/Test Events |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 6 | 1 | 18000
37 | 1 | VEM | Coordinator, Event Services |  |  | 1 |  |  |  |  | 1 |  | 1 |  | 1 |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
38 | 1 | VEM | Coordinator, Event Communications |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  | 3000 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 6 | 1 | 18000
39 | 1 | VEM | Coordinator, Signage Programming/Install |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  | 3000 | 2019-04-01 | 2019-07-31 | 0.33333 | #REF! |  | 121 | 6 | 1 | 18000
40 | 1 | VEM | Assistant, Event Services Staffing |  |  | 1 | [5 empty] | 1 | 1 |  |  |  | 2000 | 2019-03-25 | 2019-07-31 | 0.35 | #REF! |  | 128 | 6 | 1 | 12000
41 | 2 | VEM | Assistant, Signage Programming/Installation |  |  |  |  | 2 |  |  |  | 1 | 1 |  | 1 |  | 2000 | 2019-05-06 | 2019-07-31 | 0.23611 | #REF! |  | 86 | 5 | 2 | 20000 | Remove from pvt comp list
42 | 66 | VEM | Operations Manager |  |  |  |  | 66 |  |  |  | 66 | Planned |  | 66 |  | 3000 | 2019-05-06 | 2019-07-31 | 0.23611 | #REF! |  | 86 | 5 | 66 | 990000
|  |  | Sub total | 10 | 22 | 8 | 0 | 68 | 0 | 2000 | 15 | 92 | 7 | 0 | 102 | [5 empty] | #VALUE!
Event Manager (existing) | [9 empty] | 0 | [6 empty] | 1906-11-04 |  |  |  |  | Existing ven own; verify # | 0 | 1 | 20 | 50000
Existing Venue staff (mgt, stewards, etc.) | [9 empty] | 1000 | [6 empty] | 1906-11-04 |  |  |  |  | Existing venue workforce | 0 | 0.5 | 1000 | 1250000
Event Stewards | [9 empty] | tbc | [11 empty] | Work in progress
Cleaning Supervisor/Crew | [9 empty] | 1000 | [11 empty] | Cleaning/Waste companies
1 | 1 | WKM | Head of Workforce Management | 1 | [6 empty] | 1 |  | Existing |  | Existing |  | 6000 | 2018-05-15 | 2019-08-30 | 1.2917 | #REF! | A. Ronca
2 | 1 | WKM | Co-Head, Workforce Management | [5 empty] | 1 |  | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-11 | 2019-09-27 | 0.54444 | #REF! | M. Caire
3 | 1 | WKM | Manager, Volunteer Program & Uniforms | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 4000 | 2019-03-04 | 2019-09-27 | 0.56389 | #REF! | V. De Sieno |  |  |  |  | Silvia Parlato, to place
4 | 1 | WKM | Asst Mgr, Volunteers & Uniforms | 1 | [6 empty] | 1 |  | IFEL |  | 1 |  | 3500 | 2019-03-04 | 2019-08-30 | 0.48889 | #REF! | A. R. Loddo
5 | 1 | WKM | Manager, Venue Workforce Operations | 1 | [6 empty] | 1 |  | Tender |  | 1 |  | 4000 | add | 2019-08-30 | #VALUE! | #VALUE! | L. Girasole (to confirm) | #VALUE! | 6 | 1 | 24000
6 | 1 | WKM | Manager, Workforce Systems and Processing |  |  | 1 |  |  |  |  | 1 |  | Tender |  | 1 |  | 4000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 24000
7 | 1 | WKM | Manager, Training |  |  | 1 |  |  |  |  | 1 |  | Tender |  | 1 |  | 4000 | 2019-03-25 | 2019-07-31 | 0.35 | #REF! |  | 128 | 6 | 1 | 24000
8 | 1 | WKM | Coord, Volunteer Recruitment | 1 | [6 empty] | 1 |  | Tender |  | 1 |  | 3000 | 2019-02-04 | 2019-07-31 | 0.49167 | #REF! | A. Pirera | 177 | 6 | 1 | 18000
9 | 1 | WKM | Coord, Paid Staff Recruitment & Management |  |  | 1 |  |  |  |  | 1 |  | Tender |  | 1 |  | 3000 | 2019-03-11 | 2019-07-31 | 0.38889 | #REF! |  | 142 | 6 | 1 | 18000
10 | 1 | WKM | Coord, Workforce Systems and Processing |  |  | 1 |  |  |  |  | 1 |  | Tender |  | 1 |  | 3000 | 2019-03-18 | 2019-07-31 | 0.36944 | #REF! |  | 135 | 6 | 1 | 18000
12 |  |  | Coord, Workforce Planning | [13 empty] | 4000 | 2019-02-01 | 2019-07-31 | 0.5 | #REF! |  | 180 | 6 | 1
11 | 1 | WKM | Coord, Schedule Planning and Rostering |  |  | 1 |  |  |  |  | 1 |  | Tender |  | 1 |  | 3000 | 2019-03-25 | 2019-07-31 | 0.35 | #REF! |  | 128 | 6 | 1 | 18000
12 | 1 | WKM | Coord, Workforce Training |  |  | 1 |  |  |  |  | 1 |  | Tender |  | 1 |  | 3000 | 2019-03-25 | 2019-07-31 | 0.35 | #REF! |  | 128 | 5 | 1 | 15000
13 | 1 | WKM | Coord, Uniforms |  |  | 1 |  |  |  |  | 1 |  | Tender |  | 1 |  | 3000 | 2019-03-25 | 2019-07-31 | 0.35 | #REF! |  | 128 | 5 | 1 | 15000
14 | 1 | WKM | Assistant, Workforce Processing | [7 empty] | 1 |  | Tender |  | 3 |  | 2000 | add | 2019-07-16 | #VALUE! | #VALUE! | C. Truppi (to confirm) | #VALUE! | 6 | 3 | 36000
15 | 1 | WKM | Assistant, Workforce Processing |  |  | 1 |  |  |  |  | 1 |  | Tender |  | 3 |  | 2000 | 2019-04-01 | 2019-07-16 | 0.29167 | #REF! |  | 106 | 6 | 3 | 36000
|  |  | Sub total | 5 | 0 | 7 | 0 | 0 | 1 | 14 | 14 | 0 | 0 | 0 | 15 | [5 empty] | #REF! |  |  |  | 1568 | 7417000
Key
1 | Still unhired from initial IFEL offering
1 | Hired
1 | Included in Awards/Welcome/Torch tender
1 | To confirm if included in RTS or HB tender
1 | To consider adding to private company tender or to IFEL process, whichever will be faster | [9 empty] | 15 | 0 | 0 | 0 | 18 | [5 empty] | #REF! |  |  |  | 1571 | 7453000
Senior Venue Workforce Manager | [9 empty] | 14 | [11 empty] | From Vol Assoc, in tender
Uniform Distribution Supervisor | [9 empty] | 3 | [11 empty] | From Vol Assoc, in tender
#REF!
[11 empty] | 240 | 165 | 59 | 20 | 414
Napoli 2019 Staffing Plan Summary
OC Plan to Engage
|  |  |  | Hired | IFEL | Private Company | Tender | Staffing Agency | Direct (>40k) | Service Provider
|  |  | Accreditation | 1 | 1 | 0 | 7 | 3 | 0 | 0 | [10 empty] | #REF! | [5 empty] | From pvt comp hire list
|  |  | Athletes Village Management | 5 | 0 | 13 | 1 | 52 | 0 | 1290 | [10 empty] | #REF! | [5 empty] | VEM ok 7, remove 32
|  |  | Brand, Identity and Look | 1 | 0 | 1 | 0 | 0 | 0 | 111 | [10 empty] | #REF! | [5 empty] | TRA ok 5, remove 4
|  |  | Ceremonies | 1 | 0 | 0 | 4 | 0 | 0 | 300 | [10 empty] | #REF! | [5 empty] | SPT ok 5, remove 9
|  |  | Communications | 4 | 1 | 0 | 3 | 0 | 0 | 0 | [10 empty] | #REF! | [5 empty] | SEI ok 0, remove 1
|  |  | Delegation Services | 6 | 0 | 2 | 0 | 226 | 0 | 0 | [10 empty] | #REF! | [5 empty] | MBS, ok 0, remove 2
|  |  | Finance and Administration | 40 | 6 | 2 | 0 | 0 | 0 | 15 | [10 empty] | #REF! | [5 empty] | FNB, ok 1, remove 0
|  |  | Food and Beverage | 1 | 1 | 2 | 0 | 0 | 0 | 800 | [10 empty] | #REF! | [5 empty] | FIN ok 0, remove 1
|  |  | Logistics | 0 | 1 | 2 | 0 | 0 | 0 | 273 | [10 empty] | #REF! | [5 empty] | AVM ok 13, remove 9
|  |  | Marketing, Licensing & Ticketing | 7 | 0 | 0 | 4 | 0 | 0 | 399 | [10 empty] | #REF! | [5 empty] | Total = ok 31, remove 58, but could substitute 28 others in yellow; or add to IFEL list if they can hire faster?
|  |  | Media and Broadcast Services | 1 | 0 | 0 | 6 | 0 | 0 | 0 | [10 empty] | #REF!
|  |  | Medical Services & Doping Control | 5 | 0 | 0 | 2 | 0 | 0 | 328 | [10 empty] | #REF!
|  |  | Planning & C4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | [10 empty] | #REF!
|  |  | Protocol & FISU Relations | 4 | 0 | 0 | 5 | 0 | 0 | 1216 | [10 empty] | #REF! | [5 empty] | From Award/Welc/Torch tender list
|  |  | Security Integration | 1 | 1 | 0 | 0 | 0 | 0 | 2148 | [10 empty] | #REF! | [5 empty] | ACR, 7 ok, remove 0; if can engage faster than IFEL
|  |  | Sport | 8 | 4 | 5 | 2 | 149 | 0 | 243 | [10 empty] | #REF! | [5 empty] | AVM, 0 ok, remove 1 (dupe)
|  |  | Technology | 7 | 0 | 3 | 1 | 35 | 0 | 251 | [10 empty] | #REF! | [5 empty] | CER, 2 ok, remove 0
|  |  | Transportation | 2 | 5 | 12 | 0 | 6 | 0 | 2244 | [10 empty] | #REF! | [5 empty] | MAR, 4 ok, remove 0; if can engage faster than IFEL
|  |  | Venues and Infrastructure | 29 | 1 | 2 | 0 | 0 | 0 | 502 | [10 empty] | #VALUE! | [5 empty] | PFR, 5 ok, remove 0; if can engage faster than IFEL
|  |  | Venue Management | 10 | 22 | 8 | 0 | 68 | 0 | 2000 | [10 empty] | #VALUE! | [5 empty] | Host/Hostess ??
|  |  | Workforce Management | 5 | 0 | 7 | 0 | 0 | 1 | 14 | [10 empty] | #REF! | [5 empty] | Junior Secretary ??
|  |  | Sub Total | 139 | 44 | 60 | 35 | 539 | 1 | 12134 | [16 empty] | Senior Secretary ??
|  |  | Event Services (Stewards) | - | - | - | - |  | -
|  |  | Total | 139 | 44 | 60 | 35 | 539 | 1 | 12134 | [16 empty] | Total = ok 18, remove 1, but could switch to IFEL if faster
|  |  | Plan based on assumptions that OC has not validated as of 4 March 2019 | 139 | 139 |  |  | 539 | 1 |  | % hired as of 4 March
|  |  |  | 139 | 679 |  |  |  |  | To hire | 16.99%
|  |  |  | 818 | [5 empty] | Total pd
|  |  | Total space & tech equipment |  | 240 | 165 | 59 | 20 | 414
[5 empty] | ARU 1, 2 & 3 space | ARU 4 space | Desktop | Laptop | Mobile
Staffing Agency Summary
|  |  | Accreditation Center Supervisor |  |  |  |  | 3
|  |  | AV & A&D Attendant |  |  |  |  | 52
|  |  | Delegation Attache |  |  |  |  | 220
|  |  | Delegation Service Center Supervisor |  |  |  |  | 6
|  |  | Sport Information Supervisor |  |  |  |  | 25
|  |  | Team Liaison |  |  |  |  | 124
|  |  | Venue Technology Manager |  |  |  |  | 35
|  |  | Transportation Assistants |  |  |  |  | 6
|  |  | Assistant, Signage Programming/Installation |  |  |  |  | 2
|  |  | Operations Manager |  |  |  |  | 66
|  |  | Total |  |  |  |  | 539
Note on D39: Guest pass center, AV newsletter, welcome ceremonies, arrivals/departures, fitness center, etc NAP = 24, SAL = 6, CAS = 12; Del Welcome Center = 6